## Sheet1
CSI4142 - Project W23
Phase 2- Physical design and data staging
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
Create database instance | Elli | March 24th | March 24th | 1 hour | 1 hour
Create Customer dimension | Tamara | March 23rd | March 24th | 30 minutes | 1 hour
Create Location dimension | Tamara | March 24th | March 24th | 30 minutes | 1 hour
Create Product dimension | Tamara | March 24th | March 24th | 30 minutes | 1 hour
Create Shipping dimension | Tamara | March 24th | March 24th | 30 minutes | 30 minutes
Create Order dimension | Tamara | March 23rd | March 24th | 30 minutes | 30 minutes
Create Ship Date dimension | Tamara | March 23rd | March 24th | 30 minutes | 30 minutes
Create Order Date dimension | Tamara | March 24th | March 24th | 30 minutes | 30 minutes
Staging of dimension Customer | Elli, Tamara, Teodora | March 17th | March 19th | 40 minutes | 20 minutes
Staging of dimension Location | Elli, Tamara, Teodora | March 17th | March 19th | 40 minutes | 30 minutes
Staging of dimension Product | Elli, Tamara, Teodora | March 17th | March 19th | 40 minutes | 20 minutes
Staging of dimension Shipping | Elli, Tamara, Teodora | March 17th | March 19th | 40 minutes | 20 minutes
Staging of dimension Order | Elli, Tamara, Teodora | March 17th | March 19th | 40 minutes | 1 hour
Staging of dimension Ship Date | Elli, Tamara, Teodora | March 17th | March 19th | 40 minutes | 20 minutes
Staging of dimension Order Date | Elli, Tamara, Teodora | March 17th | March 19th | 40 minutes | 20 minutes
Surrogate key pipeline | Tamara | March 19th | March 21st | 2 hours | 4 hours
Staging of fact table – including FKs and measures | Tamara | March 22nd | March 23rd | 30 minutes | 45 minutes
Data quality handling and reporting | Elli, Tamara, Teodora | March 17th | March 19th | 3 hours | 6 hours
Others – if any