## Phase3-TeamPlanning2023
CSI4142 - Project 2023
Phase 4 - Data Mining
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
Data preprocessing
Data summarisation | Tamara, Teodora | March 31st | March 31st | 30min | 30min
.. Visualisation of attributes | Tamara, Teodora | March 31st | March 31st | 30min | 30min
Data transformation | Tamara, Teodora | March 31st | March 31st | 30min | 30min
.. Missing values | Tamara, Teodora | March 31st | March 31st | 30min | 10min
.. Categorical data | Tamara, Teodora | March 31st | March 31st | 30min | 30min
.. Numeric data | Tamara, Teodora | March 31st | March 31st | 30min | 15min
.. Feature selection | Tamara, Teodora | March 31st | March 31st | 30min | 15min
Data mining - Classification
Decision tree | Tamara, Elli | April 3rd | April 4th | 30min | 1hr
Gradient Boosting | Tamara, Elli | April 3rd | April 4th | 30min | 1hr
Random Forests | Tamara, Elli | April 3rd | April 4th | 30min | 45min
Comparison of results | Tamara, Elli | April 3rd | April 4th | 30min | 20min
Summary | Tamara, Elli | April 3rd | April 4th | 30min | 30min
Anomaly detection
One-class SVM | Tamara, Teodora | April 4th | April 6th | 30min | 30min
Summary | Tamara, Teodora | April 4th | April 6th | 30min | 30min
Other tasks - please specify