## Sheet1
CSI4142 - Project 2023
Phase 3- OLAP and BI Dashboard
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
OLAP queries
Drill down, roll up | Elli | 2024-04-03 | 2024-04-04 | 30 minutes | 1 hour
Slice | Elli | 2024-04-03 | 2024-04-04 | 30 minutes | 1 hour
Dice | Elli | 2024-04-03 | 2024-04-04 | 30 minutes | 1 hour
Composite OLAP - 4 queries | Elli | 2024-04-03 | 2024-04-04 | 2 hours | 3 hours
Icebergs | Elli | 2024-04-03 | 2024-04-04 | 30 minutes | 2 hours
Windowing - partition | Elli | 2024-04-03 | 2024-04-04 | 30 minutes | 1 hour
Window | Elli | 2024-04-03 | 2024-04-04 | 30 minutes | 1 hour
BI dashboard
Design of data mart | Elli | 2024-04-04 | 2024-04-05 | 30 minutes | 30 mins
Importing data | Elli | 2024-04-04 | 2024-04-05 | 30 minutes | 30 mins
OLAP queries | Elli | 2024-04-04 | 2024-04-05 | 30 minutes | 2 hours
Figures | Elli | 2024-04-04 | 2024-04-05 | 30 minutes | 1 hours
Other tasks - please specify